## OF plan
# | PO No. | Designation | Pick up location | Supplier | Country | Provence/City | Supplier Contact window | Supplier Contact email | Supplier Contact cell phone | Criticality | Schedule | As sold budget USD | Cost | Novelty to ECS | Novelty of Supplier | Kick off Meeting | Pre fab KOM | F2F KOM | Supplier Reporting Frequency | Shop Visit Frequency | Resident Expeditor | OF manhour allocation | OFM | Buyer | Engineer | SQE | Logistic | Incoterm | Planned PO release date | Revised PO release date | ActualPO release date | PO form date | PO uploaded to MTA | DL100 upload date | DL001 upload date | KoM date | Manufacturing schedule receiving date | SUMO set-up date (import delv items, responsibles, etc.) | First MPR via MTA/SUMO issue date | ITPL Status in MTA | ITPL Date Sent to Client | Transmittal Number | Status | Key Progress Milestones | Vendor design/drawing submission progress | 100% submission date | material/component procurement progress | 100% ready date | Fabrication/Assembly progress | 100% ready date | Shop test progress | Manufacture Start Date | packing & dispatch | 100% completion date | Summary | Validation of EFU list date | Pre-notice and Packing list issue date | Release for shipment (RFS) date | Forecast/Actual FAT date | Forecast/Actual ready date | Contractual ready date for FAT | Contractual delivery date with supplier | Project Need date at site / Port date | Contractual delivery date with client | Days delay | Actual delivery date | Good receipt date | Status Week 50/2019 | Status Week 49/2019 | Status Week 48 / 2019 | Status Week 47 / 2019 | Status Week 43 / 2019 | Status Week 42 / 2019 | Status Week 41 / 2019 | Status Week 40 / 2019 | Status Week 39 / 2019 | Current Status & Critical issue | Client milestone (Y/N) | Mitigation Action | Note
[44 empty] | Weight | 10% |  | 30% |  | 50% |  | 5% |  | 5% |  | 100%
1 | 4101875855 | Absorber Recycle Pump and Motor | DE | KSB SE & Co. KGaA | [5 empty] | 3 | 2 | 1810717.308 | 3 | 2 | 2 | yes | recommended | recommended | monthly |  | no |  | Tomasz Michalowski | NING Yu | WANG Maolin | ZHOU Hengwei | XU Man | FCA Workshop | 11-Jan-19 | 28-Jun-19 | 2-Aug-19 | 2019-08-05 | 2019-08-13 | 2019-08-29 | 2019-08-15 | 2019-11-18 | 2019-11-29 |  | 2019-12-15 | 2019-10-31 comments sent to KSB no response |  |  |  |  | 10% | [9 empty] | 1% | [6 empty] | 16-Sep-20 | [5 empty] | Schedule sent to Supplier | Detailed Time Schedule Sent 28-11-2019 | request sent for Detailed Time Schedule | KoM on 18.11.2019 - Time Schedule to be set till 29.11.2019 First MPR till 15.12.2019 | KoM template sent 22.10.2019 | KoM planned 12/11/2019 | GA received and uploaded | KoM to be performed - OF intervention to receive GA drawing on time | KoM to be performed - reminder sent 24/09/2019 |  | n
2 | 4101848611 | Oxidation Air Blower and Motor | IT | Howden Turbomachinery SRL | [5 empty] | 3 | 2 | 978581.2354 | 2 | 2 | 3 | yes | recommended | recommended | monthly |  | no |  | Tomasz Michalowski | Wu Jacky | ZHANG Wan | YANG Bill | XU Man | FCA Workshop | 11-Jan-19 | 31-May-19 | 17-Jun-19 | 2019-06-17 | 2019-07-01 | 2019-04-20 | 2019-07-01 | 2019-07-17 | 2019-08-29 | 2019-09-06 |  | Polish translation to be sent till end of week 50 2019-12-13 | [14 empty] | 2% | [6 empty] | 2020-09-05 | [5 empty] | Reminder sent 09-12-2019 also e-mail sent to prepare a notification for LD (ITPL) | ITPL under translation to Polish / sent request for Updated Time Schedule and MPR | ITPL under translation to Polish / sent request for Updated Time Schedule and MPR | ITPL still to be translated to Polish | ITPL approved in English. To be translated by Supplier into Polish. | ITPL under finalization (title) | Schedule accepted - MPR to be issued till 15 October | Latest revision of ITPL uploaded 30/09/2019 by Supplier to MTA | ITPL under clarification - Skype Meeting 26/09/2019
3 |  | Limestone Powder Feed System | IT/DE | [6 empty] | 3 | 2 | 185628 | 1 | 2 | 3 | yes |  | recommended | monthly |  | no |  | Tomasz Michalowski | Zhu Jianbo | WU Yang | HU Chaoyue | XU Man |  | 11-Jan-19 | 26-Nov-19 | delayed | [30 empty] | 2020-02-16
4 | 4101858197 | Gypsum Dewatering Package | CN | Shanghai Xuhe Environment Technology Co., Ltd | [5 empty] | 3 | 2 | 2318493.72 | 3 | 2 | 2 | yes | recommended | recommended | monthly |  | no |  | LIU Yang | CAO Sihan | LI Yuhui | ZHOU Hengwei | XU Man | FCA Workshop | 11-Jan-19 | 7-Jun-19 | 3-Jul-19 | 2019-07-03 | 2019-07-11 | 2019-07-22 | 2019-07-11 | 2019-07-23 | 2019-07-16 | 2019-08-05 | [6 empty] | 50% | [9 empty] | 5% | [6 empty] | 2020-09-21
5 | 4101940438 | PAC system | DE | UCC Plakon GmbH | [5 empty] | 3 | 1 | 419160 | 1 | 3 | 3 | yes |  | recommended | monthly |  | no |  | Tomasz Michalowski | Wang Shuang | LI Yuhui | ZHANG Xun | XU Man | FCA Workshop | 11-Jan-19 | 15-Nov-19 | 2019-12-05 | 2019-12-05 | [29 empty] | 2020-08-21 | [5 empty] | Time Schedule Proposal sent | PO uploaded to MTA
6 | 4101865039 | Agitators | DE | Ekato RUEhr-Und Mischtechnik GmbH | [5 empty] | 2 | 1 | 260645.664 | 1 | 2 | 2 | optional | optional | optional | monthly |  | no |  | Tomasz Michalowski | Wang Shuang | LIU Jinyin | HU Chaoyue | XU Man | FCA Workshop | 25-Jan-19 | 7-Jun-19 | 16-Jul-19 | 2019-06-16 | 2019-07-30 | 2019-08-16 | 2019-07-30 | 2019-09-03 | 2019-10-01 |  | 2019-11-27 | 2019-11-28 ROC | 2019-11-29 | GE-EHQ/CLI/T0081 | REJ |  | 25% | week 6/2020 | 50% | [7 empty] | 17.5% | [6 empty] | see as below | [5 empty] | 11-12-2019 ITPL revision sent but not accepted due to points not translated into Polish / Jakub Mitek asked for support | Detailed Time Schedule sent 03-12-2019 | request sent for Detailed Time Schedule / Schedule and MPR sent 27.11.2019 | GA drawings approved with ROC status | Approved GA drawings to be uploaded to MTA. | Quality documents list to be provided by Supplier | waiting for response from Customer / check MCL | ITPL to be released by Xiao Song to Customer | clarifiied ITPL to be upload till 25/09/2019
6.1 | item 10 | Side Entry Agitator | DE | Ekato RUEhr-Und Mischtechnik GmbH | [5 empty] | 2 | 1 | 260645.664 | 1 | 2 | 2 | optional | optional | optional | monthly |  | no |  | Tomasz Michalowski | Wang Shuang | LIU Jinyin | HU Chaoyue | XU Man | FCA Workshop | 25-Jan-19 | 7-Jun-19 | 16-Jul-19 | 2019-06-16 | 2019-07-30 | 2019-08-16 | 2019-07-30 | 2019-09-03 | 2019-10-01 |  | 2019-11-27 | 2019-11-28 ROC | 2019-11-29 | GE-EHQ/CLI/T0081 | REJ |  | 25% | week 6/2020 | 50% | [7 empty] | 17.5% | [6 empty] | 2020-11-04 | [5 empty] | 11-12-2019 ITPL revision sent but not accepted due to points not translated into Polish / Jakub Mitek asked for support | Detailed Time Schedule sent 03-12-2019 | request sent for Detailed Time Schedule / Schedule and MPR sent 27.11.2019 | GA drawings approved with ROC status | Approved GA drawings to be uploaded to MTA. | Quality documents list to be provided by Supplier | waiting for response from Customer | ITPL to be released by Xiao Song to Customer | clarifiied ITPL to be upload till 25/09/2019
6.2 | item 20 | Top Entry Agitator | DE | Ekato RUEhr-Und Mischtechnik GmbH | [5 empty] | 2 | 1 | 408012.7392 | 1 | 2 | 2 | optional | optional | optional | monthly |  | no |  | Tomasz Michalowski | Wang Shuang | LIU Jinyin | HU Chaoyue | XU Man | FCA Workshop | 25-Jan-19 | 7-Jun-19 | 16-Jul-19 | 2019-06-16 | 2019-07-30 | 2019-08-16 | 2019-07-30 | 2019-09-03 | 2019-10-01 |  | 2019-11-27 | 2019-11-28 ROC | 2019-11-29 | GE-EHQ/CLI/T0081 | REJ |  | 25% | week 6/2020 | 50% | [7 empty] | 17.5% | [6 empty] | 2020-11-04 | [5 empty] | 11-12-2019 ITPL revision sent but not accepted due to points not translated into Polish / Jakub Mitek asked for support | Detailed Time Schedule sent 03-12-2019 | request sent for Detailed Time Schedule / Schedule and MPR sent 27.11.2019 | GA drawings approved with ROC status | Approved GA drawings to be uploaded to MTA. | Quality documents list to be provided by Supplier | waiting for response from Customer | ITPL to be released by Xiao Song to Customer | clarifiied ITPL to be upload till 25/09/2019
6.3 | item 30 | Spare parts for Side Entry Agitator | DE | Ekato RUEhr-Und Mischtechnik GmbH | [5 empty] | 2 | [5 empty] | optional | optional | optional | monthly |  | no |  | Tomasz Michalowski | Wang Shuang | LIU Jinyin | HU Chaoyue | XU Man | FCA Workshop | 25-Jan-19 | 7-Jun-19 | 16-Jul-19 | 2019-06-16 | 2019-07-30 | 2019-08-16 | 2019-07-30 | 2019-09-03 | 2019-10-01 |  | 2019-11-27 | 2019-11-28 ROC | 2019-11-29 | GE-EHQ/CLI/T0081 | REJ | [11 empty] | 0% | [6 empty] | 2020-11-04 | [5 empty] | 11-12-2019 ITPL revision sent but not accepted due to points not translated into Polish / Jakub Mitek asked for support | Detailed Time Schedule sent 03-12-2019 | request sent for Detailed Time Schedule / Schedule and MPR sent 27.11.2019
6.4 | item 40 | Spare parts for Top Entry Agitator | DE | Ekato RUEhr-Und Mischtechnik GmbH | [5 empty] | 2 | [5 empty] | optional | optional | optional | monthly |  | no |  | Tomasz Michalowski | Wang Shuang | LIU Jinyin | HU Chaoyue | XU Man | FCA Workshop | 25-Jan-19 | 7-Jun-19 | 16-Jul-19 | 2019-06-16 | 2019-07-30 | 2019-08-16 | 2019-07-30 | 2019-09-03 | 2019-10-01 |  | 2019-11-27 | 2019-11-28 ROC | 2019-11-29 | GE-EHQ/CLI/T0081 | REJ | [11 empty] | 0% | [6 empty] | 2020-11-04 | [5 empty] | 11-12-2019 ITPL revision sent but not accepted due to points not translated into Polish / Jakub Mitek asked for support | Detailed Time Schedule sent 03-12-2019 | request sent for Detailed Time Schedule / Schedule and MPR sent 27.11.2019
8 | 4101879296 | Slurry Pumps and Water Pumps | DE | KSB SE & Co. KGaA | [5 empty] | 3 | 1 | 769270.0966 | 2 | 2 | 3 | yes | recommended | recommended | monthly |  | no |  | Tomasz Michalowski | NING Yu | WANG Maolin | ZHOU Hengwei | XU Man | FCA Workshop | 25-Jan-19 | 28-Jun-19 | 8-Aug-19 | 2019-08-15 | 2019-08-15 | 2019-08-29 | 2019-08-15 | 2019-11-18 | 2019-11-29 |  | 2019-12-15 | [15 empty] | 1% | [6 empty] | 15-Jan-21 | [5 empty] | Schedule sent to Supplier | Detailed Time Schedule Sent 28-11-2019 | request sent for Detailed Time Schedule | KoM on 18.11.2019 - Time Schedule to be set till 29.11.2019 First MPR till 15.12.2019 | KoM template sent 22.10.2019 | KoM planned 12/11/2019 | GA received and uploaded | KoM to be performed - OF intervention to receive GA drawing on time | KoM to be performed - reminder sent 24/09/2019
9 | 4101866753 | Absorber (Incl. Performance enhancement plate) | TR | Modul Celik Yapi Ve Petrol Sanayi Ticaret Limited Sirketi | [5 empty] | 3 | 3 | 875267.5768 | 2 | 2 | 2 | yes | recommended | recommended | monthly |  | no |  | Tomasz Michalowski | NING Yu | LIANG Meili | JIA Bin | XU Man | FCA Workshop | 25-Jan-19 | 7-Jun-19 | 17-Jul-19 | 2019-07-17 | 2019-07-19 | 2019-07-23 | 2019-07-23 | 2019-07-25 | 2019-08-07 | 2019-08-13 | 2019-08-21 | [22 empty] | see as below | [6 empty] | ITTS sent 29.11.2019 - grzegorz.nowak2@energa.pl waiting for response - inspection date 26.12.2019 / response Client will not participate in inspection | ITPL with status ROC 21.11.2019 sent to Client for Final Aproval | MPR sent 18.11.2019 and resent with questions to all departments. Info to be given till 20.11.2019 / payment to be released for material 15% | Production finished. ITPL sent to Client for approval. Date of inspection need to be agreed. Site need date - 30.01.2020 (P.Brachmański/K.Majewski). MTA training related PN/PL need to be done by CN LOG. | 14/10 - notification sent to Supplier about MPR - report delay to Management | ITPL send in Czech language / notification about inspection rejected / escalation sent 04/10/2019 | Reminder send 01/10/2019 due to no Finalized ITTPL , Detailed Updated Schedule, Date of Planned Quality Inspection | MPR to be reviewed - 25/09/2019
9.1 | item 10 | - Embedded Ring | TR | Modul Celik Yapi Ve Petrol Sanayi Ticaret Limited Sirketi | [5 empty] | 3 | 3 |  | 2 | 2 | 2 | yes | recommended | recommended | monthly |  | no |  | Tomasz Michalowski | NING Yu | LIANG Meili | JIA Bin | XU Man | FCA Workshop | 25-Jan-19 | 2019-05-20 | 17-Jul-19 | 2019-07-17 | 2019-07-19 | 2019-07-23 | 2019-07-23 | 2019-07-25 | 2019-08-07 | 2019-08-13 | 21.08.2019 / 16.09.2019 / 04.10.2019 / 18.11.2019 | 2019-11-01 ROC | 2019-11-01 | GE-EHQ/CLI/T0077 | RWC |  | 100% |  | 100% |  | 100% |  | 100% |  |  |  | 95% | [6 empty] | 27-Oct-19 | [5 empty] | Inspection at Supplier 10-12-2019 | ITTS sent 29.11.2019 - grzegorz.nowak2@energa.pl waiting for response - inspection date 26.12.2019 / response Client will not participate in inspection |  | EFU and packing list created waiting for RFS and FCA transport to site |  | 14/10 - notification sent to Supplier about MPR - report delay to Management | MPR made properly 75% end of welding 10/10/2019 | risk of not delivery on time | packing list sent 18/09/2019 to Logistic
9.2 | item 20 | - Absorber Vessel | TR | Modul Celik Yapi Ve Petrol Sanayi Ticaret Limited Sirketi | [5 empty] | 3 | 3 |  | 2 | 2 | 2 | yes | recommended | recommended | monthly |  | no |  | Tomasz Michalowski | NING Yu | LIANG Meili | JIA Bin | XU Man | FCA Workshop | 25-Jan-19 | 2019-05-20 | 17-Jul-19 | 2019-07-17 | 2019-07-19 | 2019-07-23 | 2019-07-23 | 2019-07-25 | 2019-08-07 | 2019-08-13 | 2019-08-21 | [5 empty] | 100% |  | 20% | [7 empty] | 14% | [6 empty] | 15-Feb-20 | [10 empty] | 14/10 - notification sent to Supplier about MPR - report delay to Management |  | No Updated Schedule
9.3 | item 30 | - Stairs, Platform | TR | Modul Celik Yapi Ve Petrol Sanayi Ticaret Limited Sirketi | [5 empty] | 3 | 3 |  | 2 | 2 | 2 | yes | recommended | recommended | monthly |  | no |  | Tomasz Michalowski | NING Yu | LIANG Meili | JIA Bin | XU Man | FCA Workshop | 25-Jan-19 | 2019-05-20 | 17-Jul-19 | 2019-07-17 | 2019-07-19 | 2019-07-23 | 2019-07-23 | 2019-07-25 | 2019-08-07 | 2019-08-13 | 2019-08-21 | [7 empty] | 0% | [7 empty] | 0% | [6 empty] | 12-Sep-20 | [10 empty] | 14/10 - notification sent to Supplier about MPR - report delay to Management |  | No Updated Schedule
10 |  | Antifoaming system | DE | [6 empty] | 3 | 1 | 86608.0368 | 1 | 3 | 3 | yes |  | recommended | monthly |  | no |  | Tomasz Michalowski | Wang Shuang | LI Yuhui | WANG Xiaowei | XU Man |  | 25-Jan-19 | 7-Jan-20 | [31 empty] | 2020-07-26
11 | 4101849181 | Mist Eliminator | DE | Munters Euroform Gmbh | [5 empty] | 2 | 2 | 489758.52 | 1 | 1 | 2 | optional | not required | not required | monthly |  | no |  | Tomasz Michalowski | Cao Sihan | LIU Jinyin | WANG Xiaowei | XU Man | DAP Ostroleka | 8-Feb-19 | 30-Jun-19 | 17-Jun-19 | 2019-06-19 | 2019-06-27 | 2019-07-03 | 2019-07-19 | no KoM | 2019-09-04 / 2019-10-03 | 2019-09-06 | 2019-11-16 | [5 empty] | 90% | 2019-10-18 | [8 empty] | 18% | [6 empty] | 2021-03-10 | [8 empty] | reminder sent about MPR | First MPR submitted on 16.10.2019. Progress 18%. | training 16/10/2019 to create MPR | MPR to be submited till 15 October | manufacturing schedule update received 03/10/2019 | Schedule submitted - MPR to be sent 27/09/2019 | Supplier master schedule to be submitted.
12 | 4101886891 | Absorber Spray Bank | CN | Lianyungang Zhongfu Lianzhong composites Group Co., Ltd. | [5 empty] | 2 | 2 | 538321.2 | 2 | 2 | 2 | optional | not required | optional | monthly |  | no |  | LIU Yang | NING Yu | LI Miaomiao | YANG Bill | XU Man | FCA Workshop | 8-Feb-19 | 30-Jun-19 | 27-Aug-19 | 2019-07-17: 2019-09-02; 2019-07-19: 2019-09-03; 2019-07-23: 2019-09-06 | [22 empty] | 2020-12-06
13 |  | Absorber Recycle Pump Inlet Valves | CH | [6 empty] | 3 | 1 | 212029.092 | 1 | 1 | 3 | yes |  | recommended | monthly |  | no |  | Tomasz Michalowski | Xin Qingbin | SUN Wei | WANG Xiaowei | XU Man |  | 15-Feb-19 | 2-Dec-19 | [31 empty] | 2020-07-14
14 |  | Lifting Equipment | PL | [6 empty] | 2 | 1 | 196765.68 | 1 | 1 | 2 | optional |  | optional | monthly |  | no |  | Tomasz Michalowski | Song Qitao | LIU Yang (ENG) | HU Chaoyue | XU Man |  | 20-Feb-19 | 22-Jun-20 | [31 empty] | 2020-10-03
15 | 4101903823 | Tanks | CN | Modul Celik Yapi Ve Petrol Sanayi Ticaret Limited Sirketi | [5 empty] | 2 | 1 | 502928.611 | 2 | 2 | 2 | optional |  | optional | monthly |  | no |  | Tomasz Michalowski | Fan Zeng | TBD | WANG Xiaowei | XU Man |  | 2019-05-10 | 17-Sep-19 |  | 2019-07-17: 2019-10-16; 2019-07-19: 2019-11-20 | [22 empty] | Aux Tank 07 Mar 20 other tanks 04 Jun 20
16 | bundled with boiler. | Platforms, Stairs, Walkways,with Accessories (Ladders ,Handrails, Toe PL,Bolts Misc.) | CN | [6 empty] | 2 | 1 | 186825.6 | 1 | 2 | 2 | optional |  | optional | monthly |  | no |  | SHI Yu | NING Yu | LIANG Meili | LIU Zhiqiang | XU Man |  | 2019-05-10 | TBD | [31 empty] | 2020-10-02
17 | 4101929806 | Steel Structure | CN/BG/IT | [6 empty] | 3 | 3 | 481634.9836 | 1 | 2 | 2 | yes |  | recommended | monthly |  | recommended |  | SHI Yu | NING Yu | LIANG Meili | LIU Zhiqiang | XU Man | FCA Workshop | 2019-05-10 | 30-Oct-19 | 1-Nov-2019 | 2019-07-17: 2019-11-21; 2019-07-19: 2019-11-21 | [22 empty] | 2020-05-12
17.1 | 4101585483 item 30 | Achor Bolts (bundled with Plant Anchor Bolts PO) | PL | Mostostal Kielce S A | [5 empty] | 3 | 3 |  | 1 | 2 | 2 | yes |  | recommended | weekly |  | no |  | Tomasz Michalowski | Matteo/Alicja | Gerd Kreis | LIU Zhiqiang/Karol Majewski | XU Man | DAP Ostroleka | n/a | n/a | 25 Jul 2019 | [30 empty] | 4-Mar-20
18 | 4101890088 | Recycle Slurry Piping (GRP Piping) | CN | Lianyungang Zhongfu Lianzhong composites Group Co., Ltd. | [5 empty] | 2 | 2 | 528740.4 | 2 | 2 | 2 | optional | optional | optional | monthly |  | no |  | LIU Yang | NING Yu | LI Miaomiao | YANG Bill | XU Man | FCA Workshop | 2019-05-21 | 30-Jun-19 | 29-Aug-19 | 2019-07-17: 2019-09-02; 2019-07-19: 2019-09-03; 2019-07-23: 2019-09-06 | [22 empty] | 2020-10-08
19 |  | Absorber Spray Nozzles, Quench Nozzle in the inlet of absorber (SS304L) | DE | [6 empty] | 3 | 2 | 205613.5488 | 1 | 2 | 3 | yes |  | recommended | monthly |  | no |  | Tomasz Michalowski | NING Yu | LI Miaomiao | WANG Xiaowei | XU Man |  | 2019-06-07 | 20-Sep-19 | [31 empty] | 2020-08-11
20 |  | Alloy Material | FI/IT | [6 empty] | 2 | 2 | 121616.28 | 1 | 1 | 2 | optional |  | optional | monthly |  | no |  | Tomasz Michalowski |  | LI Miaomiao | WANG Xiaowei | XU Man |  | 2019-06-07 | 2020-04-10 | [31 empty] | 2020-04-25
21 |  | Small Valves (Process & Utility Valve) | IT | [6 empty] | 3 | 1 | 393429.085 | 1 | 1 | 3 | yes |  | recommended | monthly |  | no |  | Tomasz Michalowski | Xin Qingbin | OUYANG Jian | WANG Xiaowei | XU Man |  | 2019-08-05 | 2020-07-21 | [31 empty] | 2020-06-28
22 |  | Instruments | IT | [6 empty] | 2 | 1 | 632273.0158 | 2 | 1 | 2 | optional |  | optional | monthly |  | no |  | Tomasz Michalowski | Wu Xiaohan | Liu Kangkang | HU Chaoyue | XU Man |  | 2019-08-14 | 2020-03-19 | [31 empty] | 2020-08-22
23 |  | Gas Analyzer | IT | [6 empty] | 2 | 1 | 274013.308 | 1 | 1 | 2 | optional |  | optional | monthly |  | no |  | Tomasz Michalowski | Wu Xiaohan | Liu Kangkang | HU Chaoyue | XU Man |  | 2019-08-14 | 2020-03-19 | [31 empty] | 2020-08-20
24 |  | Sulfite Analyzer | IT | [6 empty] | 1 | 1 | 51680 | 1 | 1 | 1 | no |  | no | monthly |  | no |  | Tomasz Michalowski | Wu Xiaohan | Liu Kangkang | HU Chaoyue | XU Man |  | 2019-08-14 | 2020-03-19 | [31 empty] | 2020-08-20
25 |  | Strainer | DE/IT | [6 empty] | 2 | 1 | 39520.8 | 1 | 1 | 2 | optional |  | optional | monthly |  | no |  | Tomasz Michalowski | Zhu Jianbo | LI Miaomiao | HU Chaoyue | XU Man |  | 2019-08-16 | 2020-05-10 | [31 empty] | 2020-06-23
26 |  | Control Valves | IT | [6 empty] | 2 | 1 | 573711.777 | 2 | 1 | 2 | optional |  | optional | monthly |  | no |  | Tomasz Michalowski | Xin Qingbin | Liu Kangkang | WANG Xiaowei | XU Man |  | 2019-08-26 | 2020-04-06 | [31 empty] | 2020-08-17
27 |  | Slurry GRP Piping | IT/TR | [6 empty] | 2 | 1 | 941891.7773 | 2 | 1 | 2 | optional |  | optional | monthly |  | no |  | Tomasz Michalowski | NING Yu | LI Miaomiao | YANG Bill | XU Man |  | 2019-11-06 | 2020-07-31 | [31 empty] | 2020-06-20
28 |  | Utility Piping | IT/CN | [6 empty] | 3 | 1 | 1059330.3531 | 3 | 1 | 2 | yes |  | recommended | monthly |  | no |  | Tomasz Michalowski or LIU Yang |  | TBD | WANG Xiaowei | XU Man |  | 2019-11-06 | 2020-07-30 | [31 empty] | 2020-07-06
29 |  | Instrument Hook-up Material | IT | [6 empty] | 2 | 1 | 0 | 1 | 1 | 2 | optional |  | optional | monthly |  | no |  | Tomasz Michalowski | Wu Xiaohan | Liu Kangkang | HU Chaoyue | XU Man |  | 2019-11-14 | 2020-05-15 | [31 empty] | 2020-08-17
30 |  | Lining Material (incl. application) | DE | [6 empty] | 3 | 1 | 2082626.4898 | 3 | 1 | 2 | yes |  | recommended | monthly |  | no |  | Tomasz Michalowski |  | OUYANG Jian | WANG Xiaowei | XU Man |  | 2019-12-27 | 2020-10-20 | [31 empty] | 2020-08-08
31 |  | Heat Tracing for Water Piping | PL | [6 empty] | 3 | 1 | 359280 | 1 | 2 | 3 | yes |  | recommended | monthly |  | no |  | Tomasz Michalowski |  | TBD | WANG Xiaowei | XU Man |  | 2020-01-07 | 2020-07-24 | [31 empty] | 2020-11-17
32 |  | Insulation & Cladding (Piping) | PL | [6 empty] | 3 | 1 | 967119.6308 | 2 | 1 | 3 | yes |  | recommeaded | monthly |  | no |  | Tomasz Michalowski | Zhang Jiquan | WANG Shaoliang | WANG Xiaowei | XU Man |  | 2020-03-26 | 2020-09-02 | [31 empty] | 2020-12-29
33
Other Offshore
Delivered or ready for delivery
Forecast delivery on time VS PO delivery date
Forecast Delivery late VS PO delivery date but meet client delivery date
Forecast delivery late VS PO delivery date and also client delivery date
Note on AW2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PO for raw materials placed be defined as 50% completion. Material Received be defined as 100% completion.
Note on AY2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PO for outsourced components placed be defined as 50% completion. Outsourced components received be defined as 100% completion.
Note on BA2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Manufacturing start be defined as 100%. Procurement start be defined as manufacturing start.
Note on BC2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Just input actual manufacuring progress here.

## Criticality Classification
Criticality | Level score | Definition | Remark
Schedule | 1 | Not on critical path, and not milestone related
| 2 | Not on critical path but related to internal milestone
| 3 | On critical patch
Cost | 1 | low value item (less than 500 KEUR)
| 2 | Medium value item (less than 1 MEUR but more than or equal to 500 KEUR, except top-five high value)
| 3 | High value item (More than or equal to 1 MEUR, or top-five high value)
Novelty to ECS | 1 | Standard item
| 2 | Customized but dealing with known supplier who had worked earlier for other projects
| 3 | Customized as per Technical Specification, or new equipment to ECS
Novelty of Supplier | 1 | Repeat supplier to ALSTOM, which performance is reliable
| 2 | Repeat supplier to ALSTOM, which requires regular follow up
| 3 | New Supplier Identified and 1st time to placed order